SIMVaC Retrospective Report September 16, 2005 Presented to NEMAC by Mary Lynn Manns November 11, 2005

# Timeline

# General Impressions

Most of the activity is recent

Shows a lot of growth

Shows a lot of G.I.S.  This is the most visible technical topic (but UNC-C is not here)

A lot of “first times” (new things)

No identifiable milestones showing “I finished that”

There are a lot of different things going on

There is a lot of communication across institutions

There is collaboration between community colleges that don’t traditionally do research and other institutions (UNCA)

There seemed to be positive outcomes from meetings

It’s obvious we’re not done yet

Without UNC-C at the retrospective, we are missing a part of the puzzle

There is overlap in the milestones / significant events

Define Success

I wish we could do that over again the very same way.
Why couldn’t you respond ‘yes’?...

| Issue | Suggestion for improvement |
| --- | --- |
| Money, Budget |
| Budgets got behind on balancing all budget; around beginning of 2nd year | (Now) Letter to PI’s to show total, balance, line items & instructions |
| Charlotte (CLT) budget: Concerns over cash flow | Should have indicated an experienced person in CLT (delegate) |
| Budget: Brian’s people did not handle this well | Larry’s folks to administer the budget |
| Management |
| Administration was more than expected & more than needed; Group interactions too formal |  |
| Micromanagement; are monthly reports necessary? | Quarterly reporting |
| Get professors paid on time | Check and double-check on paperwork – payroll people |
| Cohesiveness of Project |
| Too many diverse projects, hard to focus | Have to let go; prioritize |
| No knowledge of most aspects of the project; do these projects work together? | Need to make it feel like “a project” |
| No sense of what project she is a part of: no clear direction; “not in the same boat rowing”; don’t talk to each other during meetings | Need direction; (wish she was involved in wording of grant and project from the beginning) |
| Desire to know how each individual project fits together | Find more information and link the pieces together |
| Still unclear what some projects are doing | Communication with all parties: -what needed -take responsibility for roles -everyone be active |
| Group Interaction |
| Interactions between subgroups | Need scientific interactions; “where’s the beef?” |
| Didn’t think enough about administrative processes; Big picture is too diverse, hard to explain | Ship everyone to Charlotte to see what they are doing |
| Perception that this is the “Asheville Project” | Asheville go to Charlotte – show what they do |
| Agrees with the “Asheville Project” observation | Hold meetings at A-B Tech as well |
| More social events | Chocolate Fridays & more? |
| Content of Project |
| Course development should not be a part of this project – project is research-oriented, too much pressure to do course development too | Need more research aspects |
| “Define Success” continued |
| Resources (time, experience, etc.) |
| No time or resources to develop beyond our institutions |  |
| Need for Software | Need to clarify needs in future grant(s) |
| Would like things to happen faster | Remember that it’s a 2-year process; look at what’s happened so far |
| Stretched abilities beyond what Kevin felt comfortable with | Brandi has expertise, enlist her |
| Converting the data a big issue – spent a year finding data and converting it | Hope to hire someone to do training; didn’t have people who could help quickly enough |
| The Future |
| Need a plan for how to leverage SIMVaC into the future/next stage | Need a clear vision; |

# Major Errors and Costs

| Error | What it cost us |
| --- | --- |
| Slow startup | Time and focus |
| Difficulty in managing student help | A full investment from the students |
| Student involvement is not as good as it could be | Ability to engage young people |
| Didn’t break down project into cohesive unity; didn’t identify common groupings | We don’t have the kind of communication we need |
| There are places we could have worked together but didn’t | Missed opportunities |
| Individuals promised more than he/she could deliver; didn’t think about other obligations | Delay |
| Person with GIS expertise did not fit in this grant | Kevin’s sleep and an undesirable outcome |
| Didn’t involve a minority institution | Credibility |