Mgmt 380										#12

Assignment #7

25 points

DUE:  April 15

UNCA is considering building a new multipurpose athletic complex on campus.  The complex would provide a new gymnasium for intercollegiate basketball games, expanded office space, classrooms, and intramural facilities.  The following activities would need to be undertaken before construction can begin:

Activity	Description			Predecessor		Time (in weeks)

a	m	b

A		Survey building site		----			4.0	5.0	6.0

B		Develop initial design		----			2.5	3.0	3.5

C		Obtain board approval		A,B			6.0	7.0	8.0

D		Select architect		C			5.0	5.5	9.0

E		Establish budget		C			5.0	7.0	9.0

F		Finalize design		D,E			2.0	3.0	4.0

G		Obtain financing		E			8.0	10.0	12.0

H		Hire contractor		F,G			6.0	7.0	14.0

1)  Draw the project network.

2)  Identify the critical path and the expected completion time.

3)  Develop the activity schedule for the project.

4)  UNCA administration wants to know the probability that this project (the pre-construction activities) will be completed:

a)  within 21 weeks

b)  within 22 weeks

c)  within 25 weeks