Mgmt 380										#11

Assignment #7

30 points

DUE:  November 6

This is a lengthy assignment.  Start early.

You may work in teams of two.

The city of Funville is considering building a new multipurpose fun complex.  The complex would provide a new gymnasium for intercollegiate sports games, office space, a pool, and other facilities.  The following activities would need to be undertaken before construction can begin:

Activity	Description			Predecessor		Time (in weeks)

a	m	b

A		Survey building site		----			4.0	5.0	6.0

B		Develop initial design		----			2.5	3.0	3.5

C		Obtain board approval		A,B			6.0	7.0	8.0

D		Select architect		C			5.0	5.5	9.0

E		Establish budget		C			5.0	7.0	9.0

F		Finalize design		D,E			2.0	3.0	4.0

G		Obtain financing		E			8.0	10.0	12.0

H		Hire contractor		F,G			6.0	7.0	14.0

1)  Draw the project network.

2)  Identify the critical path and the expected completion time.

3)  Develop the activity schedule for the project.

4)  UNCA administration wants to know the probability that this project (the pre-construction activities) will be completed:

a)  within 34 weeks

b)  within 39 weeks